## Agile Product Backlog
SUNDEW - AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | PRIORITY | STATUS | STORY POINTS
| Design Login | Sprint 1 | Jordan Nash | 2022-12-08 | 2022-12-11 | High | Not Started | 17
1 | Implement Boostrap template | " " | " " | 2019-12-08 | 2019-12-09 | Low | Not Started | 2 | This section is for the drop-down list
2 | Design Main Menu | " " | " " | 2019-12-08 | 2019-12-09 | Low | Not Started | 2 | Yes | High | Complete
3 | Design the Login web form | " " | " " | 2019-12-10 | 2019-12-11 | High | Not Started | 13 | No | Medium | In Progress
| Design user accounts | Sprint 2 | " " |  |  |  |  | 19 |  | Low | Not Started
4 | Redesign deployment portfolio | " " | " " | 2019-12-12 | 2019-12-15 | High | Not Started | 13
5 | Design User Index web form | " " | " " | 2019-12-16 | 2019-12-17 | High | Not Started | 1
6 | Dsign My Account web form | " " | " " | 2019-12-18 | 2019-12-19 | High | Not Started | 5
| Design Job Problems | Sprint 3 | " " |  |  |  |  | 26
7 | Design User account web form | " " | " " | 2019-12-20 | 2019-12-21 | High | Not Started | 13
8 | Design Problems web form | " " | " " | 2019-12-22 | 2019-12-23 | Medium | Not Started | 5
9 | Design Job Problem web form | " " | " " | 2019-12-24 | 2019-12-25 | Medium | Not Started | 8
| Design Jobs | Sprint 4 | " " |  |  |  |  | 22
12 | Link all forms from main menu | " " | " " | 2019-12-30 | 2019-12-31 | Low | Not Started | 1
10 | Design Assign Users web form | " " | " " | 2019-12-26 | 2019-12-27 | Medium | Not Started | 8
11 | Design Jobs web form | " " | " " | 2019-12-28 | 2019-12-29 | High | Not Started | 13
| Build Database | Sprint 5 | " " |  |  |  |  | 100
12 | Setup Auth 0 | " " | " " | 2019-12-30 | 2019-12-31 | Medium | Not Started | 20
13 | Build database tables and link them up | " " | " " | 2020-01-01 | 2020-01-02 | High | Not Started | 40
14 | Input 3 sample data rows per a table | " " | " " | 2020-01-03 | 2020-01-05 | High | Not Started | 40
| Implement security features | Sprint 6 | [5 empty] | 82
15 | Brush up on tech used for project. | " " | " " | 2020-01-06 | 2020-01-12 | Low | Not Started | 2
16 | Implement CreateUser method in NewUserAccount web form | " " | " " | 2020-01-13 | 2020-01-18 | High | Not Started | 40
17 | Implement ReadUsers method in User Index web form | " " | " " | 2020-01-19 | 2020-01-24 | High | Not Started | 40
| Implement CRUD user functionality | Sprint 7 | " " |  |  |  |  | 120
18 | Implement Delete User method in | " " | " " | 2020-01-25 | 2020-01-27 | High | Not Started | 40
19 | Implement ReadUser method in User account web form | " " | " " | 2020-01-28 | 2020-01-31 | High | Not Started | 40
20 | Implement UpdateUser method in User account web form | " " | " " | 2020-02-01 | 2020-02-06 | High | Not Started | 40
| Implement User search and verification | Sprint 8 | " " |  |  |  |  | 47
21 | Implement SearchUsers method in User account web form | " " | " " | 2020-02-07 | 2020/02/012 | Low | Not Started | 2
22 | Implement Confirm_required_contact_info_provided method in User account web form | " " | " " | 2020-02-13 | 2020-02-17 | Medium | Not Started | 5
23 | Implement VerifyPassword method in User account web form | " " | " " | 2020-02-18 | 2020-02-22 | High | Not Started | 40
| Implement user search and verification part 2 | Sprint 9 | " " |  |  |  |  | 80
24 | Implement method ConfirmRequired ContactInfoProvided for User Account web form | " " | " " | 2020-02-26 | 2020-02-29 | High | Not Started | 40
25 | Ensure User system works as per specs | " " | " " | 2020-03-01 | 2020-03-07 | High | Not Started | 40
|  | " " | " "
| Create job system | Sprint 10 | " " |  |  |  |  | 81
26 | Implement method JobStartDate in the Jobs webform | " " | " " | 2020-03-08 | 2020-03-15 | Low | Not Started | 1
27 | Implement method ConfirmRequired JobInfoProvided | " " | " " | 2020-03-16 | 2020-03-18 | High | Not Started | 40
28 | Implement method CreateJob in the Jobs webform | " " | " " | 2020-03-19 | 2020-03-23 | High | Not Started | 40
| Implement CRUD ops for job system | Sprint 11 | " " |  |  |  |  | 38
29 | Implement method UpdateJob in the Jobs webform | " " | " " | 2020-03-24 | 2020-03-27 | High | Not Started | 13
30 | Implement method DeleteJob in the Jobs webform | " " | " " | 2020-03-28 | 2020-03-31 | Medium | Not Started | 5
31 | Implement method Delete_All_Job_Problems in Jobs webform | " " | " " | 2020-04-01 | 2020-04-06 | High | Not Started | 20
| Implement CRUD ops for job system part 2 | Sprint 12 | " " |  |  |  |  | 0
32 | Implement Delete_All_Job_Problems in Jobs webform | " " | " " | 2020/ |  |  | Not Started
33 | Implement DeleteAllJobChats in Jobs webform | " " | " " |  |  |  | Not Started
34 | Implement ReadJob in Jobs webform | " " | " " |  |  |  | Not Started
| Implement search and TimeDate insertion for job system part 2 | Sprint 13 | " " |  |  |  |  | 0
35 | Impement ReadJobs in Jobs webform | " " | " " |  |  |  | Not Started
36 | Implement SearchJobs in Job webform | " " | " " |  |  |  | Not Started
37 | Implement Auto_Insert_Job_Start_Date webform | " " | " " |  |  |  | Not Started
| Assigning user to job | Sprint 14 | " " |  |  |  |  | 0
38 | Implement Confirm_required_job_info_provided method in Job web form | " " | " " |  |  |  | Not Started
39 | Implement Register_User_For_Job method in Assign Users webform | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
| Implement CRUD ops for problem system | Sprint 15 | " " |  |  |  |  | 0
40 | Implement CreateProblem in Assign Jobs Problem webform | " " | " " |  |  |  | Not Started
41 | Implement UpdateProblem method in Jobs Problem webform | " " | " " |  |  |  | Not Started
42 | Implement DeleteProblem method in Jobs Problem webform | " " | " " |  |  |  | Not Started
| Implement reading and searching for problem system | Sprint 16 | " " |  |  |  |  | 0
43 | Implement ReadProblem method in Jobs Problem webform | " " | " " |  |  |  | Not Started
44 | Implement ReadProblems method in Jobs Problem webform | " " | " " |  |  |  | Not Started
45 | Implement SearchProblems method in jobs webform | " " | " " |  |  |  | Not Started
|  | Sprint 17 | " " |  |  |  |  | 0
46 | Implement Confirm Confirm_required_problem_info_provided method in Job webform | " " | " " |  |  |  | Not Started
47 | Implement Convert_problem_severity_to_text method in Job Problem webform | " " | " " |  |  |  | Not Started
48 | Implement Attach_zip_file method in Job Problem page | " " | " " |  |  |  | Not Started
|  | Sprint 18 | " " |  |  |  |  | 0
49 | Implement Attach_zip_folder method in Job Problem webform | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 19 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 20 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 20 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 20 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 20 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 20 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 20 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 20 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.