## Agile Product Backlog
SUNDEW - AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | PRIORITY | STATUS | STORY POINTS
| Design Login | Sprint 1 | Jordan Nash | 2022-12-08 | 2022-12-15 | High | In Progress | 17
1 | Implement Boostrap template | " " | " " | 2019-12-08 | 2019-12-09 | Low | Not Started | 2 | This section is for the drop-down list
2 | Design Main Menu | " " | " " | 2019-12-08 | 2019-12-09 | Low | Not Started | 2 | Yes | High | Complete
3 | Design the Login web form | " " | " " | 2019-12-10 | 2019-12-11 | High | Not Started | 13 | No | Medium | In Progress
| Design user accounts | Sprint 2 | " " |  |  |  |  | 19 |  | Low | Not Started
4 | Redesign deployment portfolio | " " | " " | 2019-12-12 | 2019-12-15 | High | Not Started | 13
5 | Design User Index web form | " " | " " | 2019-12-16 | 2019-12-17 | High | Not Started | 1
6 | Dsign My Account web form | " " | " " | 2019-12-18 | 2019-12-19 | High | Not Started | 5
| Design Job Problems | Sprint 3 | " " |  |  |  |  | 26
7 | Design user account web form | " " | " " | 2019-12-20 | 2019-12-21 | High | Not Started | 13
8 | Design Problems web form | " " | " " | 2019-12-22 | 2019-12-23 | Medium | Not Started | 5
9 | Design Job Problem web form | " " | " " | 2019-12-24 | 2019-12-25 | Medium | Not Started | 8
| Design Jobs | Sprint 4 | " " |  |  |  |  | 22
12 | Design Jobs web form | " " | " " | 2019-12-30 | 2019-12-31 | Low | Not Started | 1
10 | Design Assign Users web form | " " | " " | 2019-12-26 | 2019-12-27 | Medium | Not Started | 8
11 | Design Jobs web form | " " | " " | 2019-12-28 | 2019-12-29 | High | Not Started | 13
| Build Database | Sprint 5 | " " |  |  |  |  | 100
12 | Link all forms from main menu | " " | " " | 2019-12-30 | 2019-12-31 | Low | Not Started | 20
13 | Build database tables and link them up | " " | " " | 2020-01-01 | 2020-01-02 | High | Not Started | 40
14 | Input 3 sample data rows per a table | " " | " " | 2020-01-03 | 2020-01-05 | High | Not Started | 40
| Implement security features | Sprint 6
15 | Setup Auth 0 | " " | " " | 2020-01-06 | 2020-01-12 | High | Not Started | 40
16 | Code the User Index web form | " " | " " | 2020-01-13 |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 7 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 8 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 9 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 10 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 11 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 12 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 13 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 14 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 15 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 16 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 17 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 18 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 19 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 20 | " "
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.