## Agile Product Backlog
SUNDEW - AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | PRIORITY | STATUS | STORY POINTS
| Design Login | Sprint 1 | Jordan Nash | 2022-12-16 | 2022-12-21 | High | Not Started | 17
1 | Implement Boostrap template | " " | " " | 2019-12-16 | 2019-12-17 | Low | Not Started | 2 | This section is for the drop-down list
2 | Design Main Menu | " " | " " | 2019-12-18 | 2019-12-19 | Low | Not Started | 2 | Yes | High | Complete
3 | Design the Login web form | " " | " " | 2019-12-20 | 2019-12-21 | High | Not Started | 13 | No | Medium | In Progress
| Design user accounts | Sprint 2 | " " | 2019-12-22 | 2019-12-29 | High | Not Started | 19 |  | Low | Not Started
4 | Redesign deployment portfolio | " " | " " | 2019-12-22 | 2019-12-25 | High | Not Started | 13
5 | Design User Index web form | " " | " " | 2019-12-26 | 2019-12-27 | High | Not Started | 1
6 | Dsign My Account web form | " " | " " | 2019-12-28 | 2019-12-29 | High | Not Started | 5
| Design Job Problems | Sprint 3 | " " | 2019-12-30 | 2020-01-11 | Medium | Not Started | 26
7 | Design User account web form | " " | " " | 2019-12-30 | 2019-12-31 | High | Not Started | 13
8 | Design Problems web form | " " | " " | 2020-01-01 | 2020-01-09 | Medium | Not Started | 5
9 | Design Job Problem web form | " " | " " | 2020-01-10 | 2020-01-11 | Medium | Not Started | 8
| Design Jobs | Sprint 4 | " " | 2020-01-12 | 2020-01-20 | High | Not Started | 22
12 | Design Jobs web form | " " | " " | 2020-01-12 | 2020-01-16 | Medium | Not Started | 1
10 | Design Assign Users web form | " " | " " | 2020-01-17 | 2020-01-18 | High | Not Started | 8
11 | Link all forms from main menu | " " | " " | 2020-01-19 | 2020-01-20 | High | Not Started | 13
| Build Database | Sprint 5 | " " | 2020-01-21 | 2020-01-30 | High | Not Started | 100
12 | Setup Auth 0 | " " | " " | 2020-01-21 | 2020-01-25 | Medium | Not Started | 20
13 | Build database tables and link them up | " " | " " | 2020-01-26 | 2020-01-28 | High | Not Started | 40
14 | Input 3 sample data rows per a table | " " | " " | 2020-01-29 | 2020-01-30 | High | Not Started | 40
| Implement security features | Sprint 6 | " " | 2020-01-31 | 2020-01-24 | Medium | Not Started | 82
15 | Upgrade development machine from Windows 7 to 10. | " " | " " | 2020-01-31 | 2020-02-03 | Low | Not Started | 2
16 | Implement CreateUser method in NewUserAccount web form | " " | " " | 2020-01-13 | 2020-01-18 | High | Not Started | 40
17 | Implement ReadUsers method in User Index web form | " " | " " | 2020-01-19 | 2020-01-24 | High | Not Started | 40
| Implement CRUD user functionality | Sprint 7 | " " | 2020-01-25 | 2020-02-06 | High | Not Started | 120
18 | Implement Delete User method in | " " | " " | 2020-01-25 | 2020-01-27 | High | Not Started | 40
19 | Implement ReadUser method in User account web form | " " | " " | 2020-01-28 | 2020-01-31 | High | Not Started | 40
20 | Implement UpdateUser method in User account web form | " " | " " | 2020-02-01 | 2020-02-06 | High | Not Started | 40
| Implement User search and verification | Sprint 8 | " " | 2020-02-07 | 2020-02-22 | Low | Not Started | 47
21 | Implement SearchUsers method in User account web form | " " | " " | 2020-02-07 | 2020/02/012 | Low | Not Started | 2
22 | Implement Confirm_required_contact_info_provided method in User account web form | " " | " " | 2020-02-13 | 2020-02-17 | Medium | Not Started | 5
23 | Implement VerifyPassword method in User account web form | " " | " " | 2020-02-18 | 2020-02-22 | High | Not Started | 40
| Implement user search and verification part 2 | Sprint 9 | " " | 2020-02-26 | 2020-03-07 | High | Not Started | 80
24 | Implement method ConfirmRequired ContactInfoProvided for User Account web form | " " | " " | 2020-02-26 | 2020-02-29 | High | Not Started | 40
25 | Ensure User system works as per specs | " " | " " | 2020-03-01 | 2020-03-07 | High | Not Started | 40
|  | " " | " "
| Create job system | Sprint 10 | " " | 2020-03-08 | 2020-03-23 | High | Not Started | 81
26 | Implement method JobStartDate in the Jobs webform | " " | " " | 2020-03-08 | 2020-03-15 | Low | Not Started | 1
27 | Implement method ConfirmRequired JobInfoProvided | " " | " " | 2020-03-16 | 2020-03-18 | High | Not Started | 40
28 | Implement method CreateJob in the Jobs webform | " " | " " | 2020-03-19 | 2020-03-23 | High | Not Started | 40
| Implement CRUD ops for job system | Sprint 11 | " " | 2020-03-24 | 2020-04-06 | Medium | Not Started | 38
29 | Implement method UpdateJob in the Jobs webform | " " | " " | 2020-03-24 | 2020-03-27 | High | Not Started | 13
30 | Implement method DeleteJob in the Jobs webform | " " | " " | 2020-03-28 | 2020-03-31 | Medium | Not Started | 5
31 | Implement method Delete_All_Job_Problems in Jobs webform | " " | " " | 2020-04-01 | 2020-04-06 | High | Not Started | 20
| Implement CRUD ops for job system part 2 | Sprint 12 | " " | 2020-04-07 | 2020-04-20 | High | Not Started | 100
32 | Implement Delete_All_Job_Problems in Jobs webform | " " | " " | 2020-04-07 | 2020-04-13 | High | Not Started | 40
33 | Implement DeleteAllJobChats in Jobs webform | " " | " " | 2020-04-14 | 2020-04-16 | High | Not Started | 40
34 | Implement ReadJob in Jobs webform | " " | " " | 2020-04-17 | 2020-04-20 | High | Not Started | 20
| Implement search and TimeDate insertion for job system part 2 | Sprint 13 | " " | 2020-04-21 | 2020-04-30 | Medium | Not Started | 38
35 | Implement SearchJobs in Job webform | " " | " " | 2020-04-21 | 2020-04-23 | Low | Not Started | 5
36 | Impement ReadJobs in Jobs webform | " " | " " | 2020-04-24 | 2020-04-26 | High | Not Started | 13
37 | Implement Auto_Insert_Job_Start_Date webform | " " | " " | 2020-04-27 | 2020-04-30 | High | Not Started | 20
| Assigning user to job | Sprint 14 | " " | 2020-04-30 | 2020-05-07 | High | Not Started | 80
38 | Implement Confirm_required_job_info_provided method in Job web form | " " | " " | 2020-04-30 | 2020-05-01 | High | Not Started | 40
39 | Implement Register_User_For_Job method in Assign Users webform | " " | " " | 2020-05-02 | 2020-05-07 | High | Not Started | 40
|  | " " | " " |  |  |  | Not Started
| Create problem system | Sprint 15 | " " | 2020-05-08 | 2020-05-14 | High | Not Started | 120
40 | Implement CreateProblem in Assign Jobs Problem webform | " " | " " | 2020-05-08 | 2020-05-10 | High | Not Started | 40
41 | Implement ReadProblem method in Jobs Problem webform | " " | " " | 2020-05-11 | 2020-05-12 | High | Not Started | 40
42 | Implement ReadProblems method in Jobs Problem webform | " " | " " | 2020-05-13 | 2020-05-14 | High | Not Started | 40
| Implement reading and searching for problem system | Sprint 16 | " " | 2020-05-15 | 2020-05-23 | Medium | Not Started | 39
43 | Implement SearchProblems method in jobs webform | " " | " " | 2020-05-15 | 2020-05-17 | Medium | Not Started | 13
44 | Implement DeleteProblem method in Jobs Problem webform | " " | " " | 2020-05-18 | 2020-05-19 | Medium | Not Started | 13
45 | Implement UpdateProblem method in Jobs Problem webform | " " | " " | 2020-05-20 | 2020-05-23 | High | Not Started | 13
| Validate required job data convert problem serverity to text | Sprint 17 | " " | 2020-05-24 | 2020-05-30 | High | Not Started | 80
46 | Implement Confirm_required_problem_info_provided method in Job webform | " " | " " | 2020-05-24 | 2020-05-27 | High | Not Started | 40
47 | Implement Convert_problem_severity_to_text method in Job Problem webform | " " | " " | 2020-05-28 | 2020-05-30 | High | Not Started | 40
|  | " " | " " |  |  |  | Not Started
| Implement Attachment uploads for problem and perform Chat CRUD ops | Sprint 18 | " " | 2020-05-31 | 2020-06-13 | High | Not Started | 120
48 | Implement Attach_zip_folder method in Job Problem webform | " " | " " | 2020-05-31 | 2020-06-04 | High | Not Started | 40
49 | Implement Attach_zip_file method in Job Problem webform | " " | " " | 2020-06-05 | 2020-06-08 | High | Not Started | 40
50 | Implement CreateChat method in Job Problem webform | " " | " " | 2020-06-10 | 2020-06-13 | High | Not Started | 40
| Implement Chat CRUD ops | Sprint 19 | " " | 2020-06-14 | 2020-06-27 | High | Not Started | 101
51 | Implement Publish_chat_time_and_date method in Job Problem webform | " " | " " | 2020-06-14 | 2020-06-17 | High | Not Started | 40
52 | Implement ReadChats method in Job Problem webform | " " | " " | 2020-06-20 | 2020-06-23 | Medium | Not Started | 21
53 | Implement UpdateChat method in Job Problem webform | " " | " " | 2020-06-24 | 2020-06-27 | High | Not Started | 40
| Implement Chat CRUD ops and validate required data | Sprint 20 | " " | 2020-06-28 | 2020/06/31 | High | Not Started | 53
54 | Implement DeleteChat method in Job Problem webform | " " | " " | 2020-06-28 | 2020-06-29 | High | Not Started | 13
55 | Implement Confirm_required_info_is_not_empty method in JobProblem webform | " " | " " | 2020-06-30 | 2020/06/31 | High | Not Started | 40
|  | " " | " " |  |  |  | Not Started
| Test application | Sprint 21 | " " | 2020-06-01 | 2020-06-07 | High | Not Started | 80
56 | Input sample data into app | " " | " " | 2020-06-01 | 2020-06-03 | High | Not Started | 40
57 | Create release and reset all database primary keys to zero in release | " " | " " | 2020-06-05 | 2020-06-07 | High | Not Started | 40
|  | " " | " " |  |  |  | Not Started
| Release | Sprint 22 | " " | 2020-06-08 | 2020-06-16 | High | Not Started | 120
58 | Package app into zip | " " | " " | 2020-06-08 | 2020-06-10 | High | Not Started | 40
59 | Create user manual | " " | " " | 2020-06-11 | 2020-06-12 | High | Not Started | 40
60 | Deploy app to server enviroment | " " | " " | 2020-06-13 | 2020-06-16 | High | Not Started | 40
| Deployment | Sprint 23 | " " | 2020-06-16 | 2020-06-18 | High | Not Started | 40
61 | Show to bussiness owners | " " | " " | 2020-06-16 | 2020-06-18 | High | Not Started | 40
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 24 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 25 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 26 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.