## Agile Product Backlog
PITCHER - AGILE PRODUCT BACKLOG
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | PRIORITY | STATUS | STORY POINTS | DESCRIPTION
| Design Login | Sprint 1 | Jordan Nash | 2020-02-10 | 2020-02-14 | High | Complete | 17
1 | Implement Boostrap template | " " | " " | 2020-02-10 | 2020-02-11 | Low | Complete | 2 |  | This section is for the drop-down list
2 | Design Main Menu | " " | " " | 2020-02-12 | 2020-02-13 | Low | Complete | 2 |  | Yes | High | Complete
3 | Design the Login web form | " " | " " | 2020-02-14 | 2020-02-14 | High | Complete | 13 |  | No | Medium | In Progress
| Design user accounts | Sprint 2 | " " | 2020-02-16 | 2020-02-21 | High | Complete | 19 |  |  | Low | Not Started
4 | Redesign deployment portfolio | " " | " " | 2020-02-16 | 2020-02-17 | High | Complete | 13
5 | Design User Index web form | " " | " " | 2020-02-18 | 2020-02-19 | High | Complete | 1
6 | Dsign My Account web form | " " | " " | 2020-02-20 | 2020-02-21 | High | Complete | 5
| Design Job Problems | Sprint 3 | " " | 2020-02-23 | 2020-01-11 | Medium | Complete | 26
7 | Design User account web form | " " | " " | 2020-02-23 | 2020-02-24 | High | Complete | 13
8 | Design Jobs web form | " " | " " | 2020-02-25 | 2020-02-26 | Medium | Complete | 5
9 | Design Assign Users web form | " " | " " | 2020-02-27 | 2020-02-28 | Medium | Complete | 8
| Design Jobs | Sprint 4 | " " | 2020-03-01 | 2020-03-06 | High | Complete | 22
12 | Design Problems web form | " " | " " | 2020-03-01 | 2020-03-02 | Medium | Complete | 1
10 | Design Job Problem web form | " " | " " | 2020-03-03 | 2020-03-04 | High | Complete | 8
11 | Link all forms from main menu | " " | " " | 2020-03-05 | 2020-03-06 | High | Complete | 13
| Build Database | Sprint 5 | " " | 2020-03-08 | 2020-01-30 | High | Complete | 100
12 | Setup Auth 0 | " " | " " | 2020-03-09 | 2020-03-10 | Medium | Complete | 20
13 | Build database tables and link them up | " " | " " | 2020-03-11 | 2020-03-14 | High | Complete | 40
14 | Input 3 sample data rows per a table | " " | " " | 2020-03-16 | 2020-03-18 | High | Complete | 40
| Implement security features | Sprint 6 | " " | 2020-03-20 | 2020-03-22 | Medium | Complete | 80
16 | Implement CreateUser method in NewUserAccount web form | " " | " " | 2020-03-20 | 2020-03-23 | High | Complete | 40
17 | Implement ReadUsers method in User Index web form | " " | " " | 2020-03-27 | 2020-04-01 | High | Complete | 40
| Implement CRUD user functionality | Sprint 7 | " " | 2020-04-01 | 2020-04-03 | High | Complete | 80
19 | Implement ReadUser method in User account web form | " " | " " | 2020-04-04 | 2020-04-06 | High | Complete | 40
20 | Implement UpdateUser method in User account web form | " " | " " | 2020-04-06 | 2020-04-08 | High | Complete | 40
| Implement User search and verification | Sprint 8 | " " | 2020-04-08 | 2020-02-10 | Low | Complete | 47
21 | Implement SearchUsers method in User account web form | " " | " " | 2020-04-08 | 2020-04-10 | Low | Complete | 2
22 | Implement Confirm_required_contact_info_provided method in User account web form | " " | " " | 2020-04-13 | 2020-04-16 | Medium | Complete | 5
23 | Implement VerifyPassword method in User account web form | " " | " " | 2020-04-17 | 2020-04-19 | High | Complete | 40
| Implement user search and verification part 2 | Sprint 9 | " " | 2020-04-21 | 2020-03-07 | High | Complete | 80
24 | Implement method ConfirmRequired ContactInfoProvided for User Account web form | " " | " " | 2020-04-21 | 2020-04-23 | High | Complete | 40
25 | Ensure User system works as per specs | " " | " " | 2020-04-24 | 2020-04-27 | High | Complete | 40
|  | " " | " "
| Create job system | Sprint 10 | " " | 2020-04-27 | 2020-04-30 | High | Complete | 81
26 | Implement method JobStartDate in the Jobs webform | " " | " " | 2020-04-27 | 2020-04-29 | Low | Complete | 1
27 | Implement method ConfirmRequired JobInfoProvided | " " | " " | 2020-05-01 | 2020-03-18 | High | Complete | 40
28 | Implement method CreateJob in the Jobs webform | " " | " " | 2020-03-19 | 2020-03-23 | High | Complete | 40
| Implement CRUD ops for job system | Sprint 11 | " " | 2020-03-24 | 2020-04-06 | Medium | Complete | 38
29 | Implement method UpdateJob in the Jobs webform | " " | " " | 2020-03-24 | 2020-03-27 | High | Complete | 13
30 | Implement method DeleteJob in the Jobs webform | " " | " " | 2020-03-28 | 2020-03-31 | Medium | Complete | 5
31 | Implement method Delete_All_Job_Problems in Jobs webform | " " | " " | 2020-04-01 | 2020-04-06 | High | Complete | 20 | Aborted.
| Implement CRUD ops for job system part 2 | Sprint 12 | " " | 2020-04-07 | 2020-04-20 | High | Complete | 100
32 | Implement Delete_All_Job_Problems in Jobs webform | " " | " " | 2020-04-07 | 2020-04-13 | High | Complete | 40 | Aborted.
33 | Implement DeleteAllJobChats in Jobs webform | " " | " " | 2020-04-14 | 2020-04-16 | High | Complete | 40
34 | Implement ReadJob in Jobs webform | " " | " " | 2020-04-17 | 2020-04-20 | High | In Progress | 20
| Implement search and TimeDate insertion for job system part 2 | Sprint 13 | " " | 2020-04-21 | 2020-04-30 | Medium | Complete | 38
35 | Implement SearchJobs in Job webform | " " | " " | 2020-04-21 | 2020-04-23 | Low | Complete | 5
36 | Impement ReadJobs in Jobs webform | " " | " " | 2020-04-24 | 2020-04-26 | High | Complete | 13
37 | Implement Auto_Insert_Job_Start_Date webform | " " | " " | 2020-04-27 | 2020-04-30 | High | Complete | 20 | Decided to manually implement job start. No automation.
| Assigning user to job | Sprint 14 | " " | 2020-05-01 | 2020-05-03 | High | Complete | 80
38 | Implement Confirm_required_job_info_provided method in Job web form | " " | " " | 2020-05-01 | 2020-05-03 | High | Complete | 40
39 | Implement Register_User_For_Job method in Assign Users webform | " " | " " | 2020-05-06 | 2020-05-09 | High | Complete | 40
|  | " " | " "
| Create problem system | Sprint 15 | " " | 2020-05-10 | 2020-05-14 | High | In Progress | 120
40 | Implement CreateProblem in Assign Jobs Problem webform | " " | " " | 2020-05-10 | 2020-05-13 | High | Complete | 40 | Decided to not implement feature. Not needed right now.
41 | Implement ReadProblem method in Jobs Problem webform | " " | " " | 2020-05-16 | 2020-05-19 | High | In Progress | 40
42 | Implement ReadProblems method in Jobs Problem webform | " " | " " | 2020-05-22 | 2020-05-25 | High | Complete | 40
| Implement reading and searching for problem system | Sprint 16 | " " | 2020-05-15 | 2020-05-23 | Medium | Complete | 39
43 | Implement SearchProblems method in jobs webform | " " | " " | 2020-05-25 | 2020-05-28 | Medium | Complete | 13
44 | Implement DeleteProblem method in Jobs Problem webform | " " | " " | 2020-05-30 | 2020-06-03 | Medium | Complete | 13 | Decided to not implement feature. Not needed right now.
45 | Implement UpdateProblem method in Jobs Problem webform | " " | " " | 2020-06-06 | 2020-06-09 | High | Complete | 13 | Decided to not implement feature. Not needed right now.
| Validate required job data convert problem serverity to text | Sprint 17 | " " | 2020-06-09 | 2020/06/ | High | Not Started | 80
46 | Implement Confirm_required_problem_info_provided method in Job webform | " " | " " | 2020-06-10 | 2020-06-12 | High | Complete | 40
47 | Implement Convert_problem_severity_to_text method in Job Problem webform | " " | " " | 2020-06-11 | 2020-05-18 | High | Not Started | 40
|  | " " | " "
| Implement Attachment uploads for problem and perform Chat CRUD ops | Sprint 18 | " " | 2020-05-19 | 2020-06-13 | High | Not Started | 120
48 | Implement Attach_zip_folder method in Job Problem webform | " " | " " | 2020-05-18 | 2020-06-25 | High | Not Started | 40
49 | Implement Attach_zip_file method in Job Problem webform | " " | " " | 2020-06-28 | 2020/06/31 | High | Not Started | 40
50 | Implement CreateChat method in Job Problem webform | " " | " " | 2020-06-10 | 2020-06-13 | High | Not Started | 40
| Implement Chat CRUD ops | Sprint 19 | " " | 2020-06-14 | 2020-06-27 | High | Not Started | 101
51 | Implement Publish_chat_time_and_date method in Job Problem webform | " " | " " | 2020-06-14 | 2020-06-17 | High | Not Started | 40
52 | Implement ReadChats method in Job Problem webform | " " | " " | 2020-06-20 | 2020-06-23 | Medium | Not Started | 21
53 | Implement UpdateChat method in Job Problem webform | " " | " " | 2020-06-24 | 2020-06-27 | High | Not Started | 40
| Implement Chat CRUD ops and validate required data | Sprint 20 | " " | 2020-06-28 | 2020/06/31 | High | Not Started | 53
54 | Implement DeleteChat method in Job Problem webform | " " | " " | 2020-06-28 | 2020-06-20 | High | Not Started | 13
55 | Implement Confirm_required_info_is_not_empty method in JobProblem webform | " " | " " | 2020-06-30 | 2020-07-02 | High | Not Started | 40
|  | " " | " " |  |  |  | Not Started
| Test application | Sprint 21 | " " | 2020-07-04 | 2020-06-07 | High | Not Started | 80
56 | Input sample data into app | " " | " " | 2020-07-04 | 2020-07-05 | High | Not Started | 40
57 | Create release and reset all database primary keys to zero in release | " " | " " | 2020-07-06 | 2020-07-09 | High | Not Started | 40
|  | " " | " " |  |  |  | Not Started
| Release | Sprint 22 | " " | 2020-07-10 | 2020-06-10 | High | Not Started | 120
58 | Package app into zip | " " | " " | 2020-07-10 | 2020-07-12 | High | Not Started | 40
59 | Create user manual | " " | " " | 2020-07-13 | 2020-07-15 | High | Not Started | 40
60 | Deploy app to server enviroment | " " | " " | 2020-07-17 | 2020-07-19 | High | Not Started | 40
| Deployment | Sprint 23 | " " | 2020-07-21 | 2020-07-24 | High | Not Started | 40
61 | Show to bussiness owners | " " | " " | 2020-07-21 | 2020-07-24 | High | Not Started | 40
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 24 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 25 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | Sprint 26 | " " |  |  |  |  | 0
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started
|  | " " | " " |  |  |  | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.